## Sheet1
Task Group | Detailed task | Assingned | Progress | Description
Create Scenes | Add scene functionality to game manager |  | Done | In more advanced games we would probably make a sepperate scene class where we will can organise everything in a "scene". In this case we will probably just hard-code it with the menu for simplicity. We need to update the game manager to have a variable telling it what scene it is currently on, and then the display, click etc functions will been to be updated with if statements to display the appropriate objects in the scene.
| Split display function between scenes |  | Done
Main menu | Impliment button class | Charlie | Done | Like the square class, this will be a class for each button we will use (mostly in the menu but everywhere else will use the same class - infact the squares could have been done as buttons, but we will be keeping them separate for animation purposes) They will need a "click" function, display, etc. Functions: Display, Click, IsIn
| Impliment menu class | Ben | Done | The menu will be like a board, holding lots of buttons which each do different things. We will have to think and decide how to resolve each click and move to each menu. We may do it with delegates which is a new concept
| Impliment menu scene | Ben | Done | Add the scene!
| Add menu buttons | Charlie | In progress | Make all the buttons
| Finish main menu | Charlie | In progress | Make all the correct scene changes (level, arcade, settings) and positioning.
| Finish complete game menu | Ben | In progress | Make two buttons, ("next level" and "Quit") - and scene changes/positioning. Pluss add gray out - new class
Game levels | Create different level scenes |  |  | Make a separate scene for each type of level.. Or maybe one scene with different settings for the type of level?
| Impliment timer |  |  | Just like the move counter but have it tick regularly.
| Impliment game-over scene |  |  | Part of the game or scene possibly, we will have to think about it
Settings | Create settings class |  |  | Same as menu! It will be another class like it
| Add all settings as global variables |  |  | We will need to add the settings as menus
| Create settings scene |  |  | Create a scene for the settings!
Music | Create music player class |  |  | Research and find a good music playing library for python. Then make a class to handle that - so if we ever change the class the only code we need to change is the music player class not anything else
| Play respective music on each menu |  |  | Add it to the rest of the game!
Graphics | Make pictures! |  |  | Graphic design time!
| Replace with pictures! |  |  | Add them all in!
| Animations |  |  | This will be an extra thing we may do at the end if we have time
Board updates | Make the board scale |  |  | Edit the board scaling function to have the distances scale as well
Exporting for Mobile |  |  |  | Find a library to export our game to work as an app on Android
Fix font problem